## PhDTimelinePlanner
PhD Timeline | 2018 |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July
ENG Admin | 2019 May: 15MAY: Reading list due; 2019 June: 01JUN: Progress Report due; 2019 Aug: 27AUG: Submit written notification; 2019 Sep: 4SEP: Submit List of Texts of Interest; 2019 Oct: 10OCT: Meet Chair of Major Field Exam Committee; 2019 Dec: Focused Field Exam admin (see note); 2020 Jan: 17JAN: Focused Field Reading List due; 2020 Feb: 10FEB: Written notice of Focused Field Exam due, and more (see notes); 2020 Mar: 25MAR: Meet Chair of Focused Field Exam; 2020 June: 01JUN: Progress Report due; 2020 Aug: AUG: Form Dissertation Committee; 2020 Dec: 23DEC: Submit Eng. Dept. Prospectus Approval form; 2021 Feb: Begin Ethics; 2021 June: 01JUN: Eng. Dept. Progress Report due; 2022 July: Program Complete
SSHRC Admin | 2019 Aug: 19AUG: Annual progress report due; 2020 Aug: 17AUG: Annual progress report due; 2021 Aug: 16AUG: Final progress report due
Coursework | 2018 Sep: First term (05SEP-22DEC); 2019 Jan: Second term (07JAN-10APR)
Readings | 2019 June: Begin reading for Major Field; 2019 Dec: Begin reading for Focus Field
Exams, Conference, and Defence | 2019 Nov: 12NOV: Major Field Exam (Oral Ex on 25NOV); 2020 Apr: 7-9APR: Focus Field Exam (Oral Ex TBD); 2020 Dec: 23DEC: Submit Dissertation Prospectus; 2021 Jan: 20JAN: Conference; 2021 Feb: 03FEB: Submit Memorandum; 2022 May: 15MAY: Language exam; 2022 Jun: 21JUN: Defense
Dissertation project | 2021 Feb: Project prep; 2021 Mar: Academic writing (drafting); 2021 Apr: Academic writing (drafting); 2021 May: Academic writing (drafting); 2021 June: Academic writing (drafting); 2021 Aug: Begin Haptic Map and blog about it; 2021 Sep: Begin interviews for podcast; 2021 Oct: Sign off on academic writing portion; 2022 Jan: Complete podcast interviews; 2022 Feb: Podcast post-production; 2022 Apr: Complete Haptic Map; sign off on Blog content
Language requirement | 2022 Jan: Language-exam study begins
Paid work | 2018 Sep: 7hrs/week average until end of second term; 2019 Apr: Full-time (~30/wk); 2019 June: 10-31JUN: Vacation; 2019 Jul: Full-time (~30/wk); 2021 Jan: Average 8hrs/week until around August; 2021 Aug: Check on remaining Coldesp funds; 2022 July: Get a job: you're a grownup, now.
Holidays | 2019 June: At conference 16-26JUN; 2019 Jul: Vacation in Europe 25JUL-10AUG; 2020 May: Post-traumtic exam leave (May 11-Aug 5); 2020 June: Post-traumtic exam leave (May 11-Aug 5); 2020 Jul: Post-traumtic exam leave (May 11-Aug 5); 2021 Jul: Holiday? (July 3-31); 2021 Dec: 2 weeks over Xmas/New Year's
PhD program outcomes | bar: 2018 Sep
Actual deliverables | 2018 Sep: Coursework; 2018 Oct: Comprehensive and Prospectus exams; 2018 Nov: Language requirement; 2018 Dec: Dissertation (academic writing, blog, podcasts, haptic map installation)
Existential compass reminders | 2018 Sep: Collaborate, don't debate; 2018 Oct: Think "contracolonial"; 2018 Nov: Be public-facing; 2018 Dec: Check-in with allies; 2019 Jan: Create spaces; 2019 Feb: Get out of the way; 2019 Mar: Bring and leave good feelings; 2019 Apr: Listen and ask, don't show and tell; 2019 May: Build empathy
Note on R3: Submit Focused Field Reading List and Statement, with approval form signed by all Examining Committee members, to Graduate Secretary (60 working days prior to anticipated exam date).
Note on S3: Submit written notification of Focused Field Examination date and format to Graduate Secretary (45 working days prior to exam). Feb. 10: Finalize reading list on which you want to be examined. No later than Feb. 10 (40 working days before): Submit statement and reading list (of 25 book-equivalents) to Grad Secretary. Inform Grad Sec of date you wish to write and choice of format for exam.
Note on T3: Meet with Chair of Focused Field Examining Committee to discuss format of examination question paper (15 working days prior to exam).
Note on M4: This form: https://www.uvic.ca/graduatestudies/assets/docs/docs/2018%20Progress_Report%20Form_fillable.pdf -K Shortreed
Note on Y4: This form: https://www.uvic.ca/graduatestudies/assets/docs/docs/2018%20Progress_Report%20Form_fillable.pdf -K Shortreed
Note on P7: WRITE MAJOR FIELD CANDIDACY EXAMINATION*. Oral examination to be held within 10 working days. *Note that examination categories (of genre, methodology or critical focus) should be determined by the Examining Committee, in consultation with the student, well in advance of the exam date (see section 7.8.3). Note that while the university allows a seven year period for the completion of a Ph.D., we strongly recommend that students aim to complete within four or five years.
Note on U7: WRITE FOCUSED FIELD CANDIDACY EXAMINATION*. Oral examination to be held within 10 working days.
Note on AC7: Submit Dissertation Prospectus to English Graduate Secretary
Note on AT7: Cannot sit final ORAL EXAM until LANGUAGE EXAM complete. In 2019, for example, it ran in mid-July.
Note on AU7: 7.10 THE FINAL ORAL EXAMINATION In order to meet convocation deadlines, Graduate Studies recommends that Ph.D. orals be held no later than July 8 (for Fall convocation) or March 1 (for Spring convocation). To ensure the completed dissertation meets the necessary requirements, students should familiarize themselves with information available on the Graduate Studies website well in advance of preparing the final dissertation and submitting a Request for Oral. Students will be allowed to proceed to the Final Oral Examination (also known as the Defense) after having satisfied all other requirements for the Ph.D. degree (including the language requirement).
Note on Y10: Formal Constitution of Dissertation Supervisory Committee.
Note on AI10: Chapter one submitted to supervisor (mandatory requirement for students entering program on or after September 2018).
Note on J11: From Handbook: Notify Graduate Secretary of Major Field Examination Area and Major Field Examining Committee Members
Note on K11: 2-3wks in June,TBD
Note on A14: Personal notes to myself about my broader goals for even doing a PhD in the first place. Think of these as guiding principles.